## Pilot Plan
CJP AI Persona — Pilot Execution Plan (3 weeks, 2-person)
<100-doc pilot . Pao leads implementation (Claude Code) . Sheena supports (prep, curation, eval, docs)
OBJECTIVE
Prove, on a curated subset of fewer than 100 documents, that the hybrid retrieval + Sonnet composition pipeline produces high-fidelity, in-voice CJP responses with acceptable latency and an improving cost-per-query, before scaling to the full 1,000+ document corpus.
TEAM & WORKING MODEL
Pao - implementation lead | Owns the code path via Claude Code: repo, chunking, embeddings, sparse arm, fusion, routing, composer, payload slimming, caching, evals.
Sheena - support | Corpus prep & normalisation QA, pilot doc-set curation, exemplars, eval-set authoring, output verification, metrics recording, document deliverables (Cowork).
Working pattern | Two parallel tracks with hand-offs: Sheena prepares/curates and verifies what Pao builds; Pao consumes Sheena's frozen inputs. Respect the Depends order.
SCOPE SPLIT (full corpus vs pilot subset)
Taxonomy = full corpus | The topic map, clustering, centroids and independence check are built on the FULL ~1,000-doc corpus, so topic structure, orphaned content and empty topics are seen accurately - a 100-doc slice would distort them (a topic may look orphaned at 100 but be well-populated at 1,000).
Pilot run/eval = <100 | The pipeline is RUN and EVALUATED on the curated <100 subset, tagged against the full taxonomy. Small = fast to iterate and hand-checkable for grounding/fabrication. Composer latency & cost are per-query, independent of corpus size.
ARCHITECTURE AT A GLANCE
Offline build | Normalised UTF-8 corpus; heading-aware chunks + doc store keyed by doc_id; dense embeddings; BM25 sparse index + curated keyword/entity dictionary; topic centroids; date index; Voice Card.
Runtime - code | Query embed -> centroid scoring -> theme/topic routing; hybrid fusion (dense + sparse, RRF) -> top-k chunks; deterministic register + disclaimer selection. No LLM in this path.
Retrieval principle | Topics BIAS retrieval (a soft prior + register/disclaimer driver); PASSAGES decide (passage-level ranking); the sparse arm rescues exact identifiers. Topics never hard-gate retrieval - a routing error must not hide the right passage.
Runtime - Sonnet | Composition only: slim payload (top-k chunks + lean directives + cached Voice Card prefix) -> ENVELOPE. Streamed.
Embedding model | all-MiniLM-L6-v2 local @384d (lowest latency, zero per-call cost), or text-embedding-3-small @256-512d if hosted preferred. Same model for docs, queries, centroids.
Biggest cost lever | Payload slimming (chunks not whole docs) + prompt-caching the static prefix - not the embedding model or the router.
LATENCY / COST GUARDRAILS (from architecture review)
Measure p95 & TTFT | Track p95 and time-to-first-token, not just medians - the worst-case paths (fallback double-call, cold start, cache miss, API variance) inflate p95, not the median you look at first.
Output side too | Output tokens drive cost/latency as much as input: cap max_tokens, give the Voice Card length discipline, and stream prose (don't wrap the visible answer in JSON).
Treat as gates | Expand-on-demand fire-rate (target < ~10%) and cache-hit rate are release gates; default top-k starts low and rises only when recall@k demands it.
PHASE SUMMARY (3 weeks)
Week | Theme & focus
Week 1 | Foundation + hybrid retrieval (two weeks condensed) - stabilise, normalise corpus, freeze the <100 pilot subset, chunk + embed, sparse arm + keyword dictionary, taxonomy on the FULL corpus, fusion + code routing, latency baseline, decisions memo.
Week 2 | Composition, payload slimming & guardrails - Sonnet composer + ENVELOPE, slim payload, prefix caching, date index, threshold + theme-as-control-signal disclaimer, expand-on-demand.
Week 3 | Evaluate, tune & decide - eval set, quality + latency/cost evals, payload sweep to the knee, fusion/threshold tuning, pilot report + Go/No-Go, ADRs.
NOTE ON WEEK 1 LOAD
Week 1 intentionally carries two weeks of build scope. It is feasible only because the two tracks run in parallel and Claude Code accelerates implementation. The full-corpus taxonomy (W1.7) is foundational and should not slip; if pressure mounts, the safest items to push into Week 2 are the centroid independence REVIEW (the merge/sharpen pass within W1.7) and the register classifier (part of W1.8) - both refinements, not core-path blockers.

## Weekly Tasks
Weekly Task Tracker - CJP AI Persona Pilot (<100 docs) . 3-week, 2-person playbook (Pao + Sheena)
Pao = implementation (Claude Code). Sheena = support: prep, curation, verification, docs (Cowork). Subtasks tagged [Pao]/[Sheena]. Update Status as you go.
ID | Week | Task | Subtasks (with owner) | Lead | Claude Code / Cowork prompt (paste-ready) | Result / acceptance | Status
W1.1 | Week 1 | Stabilise the codebase | - Audit branches; find latest working runtime state [Pao] - Consolidate to one clean branch; resolve conflicts [Pao] - Tag baseline 'pilot-baseline'; set up pilot working dir [Pao] - Confirm end-to-end run; document env/setup steps [Sheena] | Pao | Open the repo (Supervaise-Reachy-Mini-Project). Audit branches, find the latest working runtime pipeline, consolidate to one clean working branch, resolve conflicts, tag 'pilot-baseline', and confirm an end-to-end run. Output a short changelog and the env/setup steps to run it. | Single clean branch; baseline tagged; run steps documented. | Not started
W1.2 | Week 1 | Normalise & prep the corpus | - Write normalisation script: mojibake->UTF-8, quotes/dashes [Pao] - Safely parse JSON-list fields; casefold/strip keywords [Pao] - Re-save utf-8-sig, ensure_ascii=False [Pao] - Run on all curated CSVs; QA rows changed; spot-check 10 docs [Sheena] - Log unparseable fields for follow-up [Sheena] | Pao | Write/run a normalisation script for the curated CSVs (e.g. cjp_columns_curated.csv): fix cp1252 mojibake (0x97 em-dash, 0x91-0x94 smart quotes, 0x9d) to UTF-8, normalise curly quotes/dashes to ASCII, safely parse JSON-list fields (Keyword/s, primary_topics, sub_topics, signature_phrases, entities), casefold/strip keyword tokens, re-save as utf-8-sig with ensure_ascii=False, and report rows changed + unparseable fields. | Clean UTF-8 corpus; mojibake=0; QA report; issues logged. | Not started
W1.3 | Week 1 | Freeze the <100 pilot/eval subset | - Select <100 docs across themes A-E + all formats - this is the pilot RUN/eval set [Sheena] - Deliberately include AI-governance + orphaned-topic docs [Sheena] - Produce doc_id list + 1-line rationale each [Sheena] - Coverage check; flag thin themes/formats [Sheena] - Note: subset is tagged against the FULL taxonomy built in W1.7 [Sheena] | Sheena | From the normalised corpus, propose a representative pilot subset of <100 docs spanning themes A-E and all formats. This is the set the pilot RUNS and is EVALUATED on - NOT the taxonomy-design set (that is the full corpus, W1.7). Deliberately include the AI-governance content and any orphaned-topic docs. Output a frozen doc_id list with a one-line rationale each and a coverage table; the subset will be tagged against the full taxonomy from W1.7. | Frozen <100 doc_id list + coverage handed to Pao. | Not started
W1.4 | Week 1 | Chunk corpus + doc store | - Heading-aware chunking (~200-400 tokens, small overlap) [Pao] - Doc store keyed by doc_id -> {chunks, metadata} [Pao] - chunk_id -> doc_id map [Pao] - Attach anecdotes/signature_phrases to doc_id metadata [Pao] - Spot-check chunk boundaries on 5 docs [Sheena] | Pao | Implement heading-aware chunking of each pilot .md into sections (~200-400 tokens, small overlap). Build a doc store keyed by doc_id -> {chunks, metadata: theme, topics, date front-matter, source} with a chunk_id->doc_id map. Keep anecdotes and signature_phrases attached to doc_id metadata so they survive payload slimming. | Doc store + chunk index; anecdotes retained; boundaries verified. | Not started
W1.5 | Week 1 | Embed the pilot subset (runtime index) | - Load chosen model (all-MiniLM-L6-v2 @384d, swappable) [Pao] - Load model ONCE at service start (resident) - never per-request, to avoid cold-start spikes [Pao] - Embed the <100 subset chunks; numpy float32 matrix + persist [Pao] - Same model/dim for queries, centroids & full-corpus taxonomy (W1.7) [Pao] - Apply search_query/search_document types if supported [Pao] | Pao | Embed the <100 pilot-subset chunks with all-MiniLM-L6-v2 @384d (keep the model swappable) to build the runtime retrieval index. Load the embedding model ONCE at service start and keep it resident (never per-request) to avoid cold-start latency spikes. Store vectors in an in-memory numpy float32 matrix indexed by chunk_id, persisted to .npy + json. Use the SAME model/dim here, for queries, for centroids, and for the full-corpus taxonomy embedding in W1.7. | Pilot-subset index embedded, persisted, resident-loaded and queryable. | Not started
W1.6 | Week 1 | Build the sparse arm (BM25) | - BM25 index over full chunk text [Pao] - Load curated keywords+entities as atomic-phrase dictionary [Pao] - Keep multi-word keywords as single terms (no whitespace split) [Pao] - Expose sparse_score(query) -> ranked chunk_ids [Pao] | Pao | Build a BM25 index over full chunk text. Load the normalised curated Keyword/s + entities as an atomic-phrase boost dictionary - treat each multi-word keyword as a single term (do NOT whitespace-tokenise; 91% are multi-word). Expose sparse_score(query) returning ranked chunk_ids. | BM25 + keyword dictionary returns ranked chunks. | Not started
W1.7 | Week 1 | Taxonomy on the FULL corpus + tag subset | - Embed the full ~1,000-doc corpus offline (cheap with MiniLM) [Pao] - Cluster; map clusters to the 38 topics; flag orphaned clusters / empty topics [Pao] - Build topic centroids from full-corpus exemplars [Pao] - Pairwise cosine; flag pairs >0.85 to merge/sharpen [Pao] - Review clusters + merges; confirm final topic set [Sheena] - Tag the <100 pilot subset against the final taxonomy [Pao] | Both | Design the taxonomy on the FULL corpus (not the subset): embed all ~1,000 docs offline with the same MiniLM model, cluster them, map clusters to the 38 topics, and flag orphaned clusters (candidate new topics) and empty topics (merge/drop). Build per-topic centroids = normalised mean of [topic label + description + signature_phrases + full-corpus exemplar chunks]. Compute pairwise centroid cosine, flag pairs >0.85 to merge/sharpen, and assign topics by similarity threshold (1-3 primary + secondary, no fixed count). Finally tag the <100 pilot subset against this final taxonomy. | Full-corpus taxonomy + centroids built; pilot subset tagged against it. | Not started
W1.8 | Week 1 | Hybrid fusion + code routing (soft prior) | - Query embed -> centroid scoring -> softmax + out-of-scope threshold [Pao] - Rank at PASSAGE level: score = passage_sim + lambda*topic_affinity (topics BIAS, never gate) [Pao] - Fallback to global subset search when top topic score is weak / near-tied [Pao] - RRF fusion of dense + sparse -> top-k chunk_ids (sparse rescues exact identifiers) [Pao] - Remove Haiku router (no LLM in path) [Pao] - Deterministic register classifier (theme table + query cues) [Pao] - Hand-label register on eval queries; score classifier [Sheena] | Pao | Replace the Haiku router with code: embed query -> score vs topic centroids -> softmax + out-of-scope threshold -> theme + topic_paths. IMPORTANT: topics BIAS retrieval, they do NOT gate it - rank candidates at the PASSAGE level by score = passage_similarity + lambda*topic_affinity (a small boost, not a pre-filter), and fall back to global subset search when the top topic score is weak or two topics are near-tied (so a routing error never hides the right passage). Implement hybrid retrieval = reciprocal rank fusion of dense (cosine) + sparse (BM25) -> top-k chunk_ids; the sparse arm rescues exact identifiers (EEZ, Article XII Section 2, JMSU) that topic/passage vectors blur. Add a deterministic register classifier (theme->register table + query-cue rules) over {ceremonial_doctrinal, case_analytical, testimonial, ceremonial_with_humor, reflective_pedagogical, META}. No LLM in this path. | Passage-level ranking with topic soft-prior + global fallback; fusion + register classifier working. | Not started
W1.9 | Week 1 | Latency logging + baseline | - Per-stage timing (input gate->router->retrieval->composer) [Pao] - Capture time-to-first-token (TTFT) separately from total [Pao] - JSON-lines logs + p50/p95 summary script (report p95, not just median) [Pao] - Warm the model/service before measuring (steady-state, not cold) [Pao] - Run baseline on current pipeline over draft queries [Pao] - Record baseline latency/TTFT/cost/quality to Pilot Metrics [Sheena] | Both | Add per-stage timing (ASR if present -> input gate -> router -> retrieval -> composer) emitting JSON-lines logs, plus a script summarising p50/p95 per stage. Capture time-to-first-token separately from total latency and report p95 (not just median). Warm the model/service before the baseline run so you measure steady-state, not cold-start. Run the frozen pilot set through the current pipeline and write baseline latency (e2e + per-stage + TTFT), cost/query and quality to baseline.json. | Per-stage + TTFT logging live; warmed baseline (p50/p95) recorded. | Not started
W1.10 | Week 1 | Lock decisions memo | - Record embedding model, store, hybrid architecture [Sheena] - Record routing + theme-as-control-signal decisions [Sheena] - Set latency/quality/cost targets in Pilot Metrics [Sheena] - Circulate for sign-off [Sheena] | Sheena | Draft a one-page Week-1 Decisions memo: embedding model (all-MiniLM-L6-v2 @384d / text-embedding-3-small @256-512d), in-memory numpy retrieval, hybrid dense+sparse(BM25)+keyword dictionary, centroid topic dimensions, deterministic code routing, theme-as-control-signal, and latency/quality/cost targets. One decision per row with rationale + owner. | Decisions memo signed off; targets entered. | Not started
W2.1 | Week 2 | Sonnet composer + ENVELOPE (guardrails) | - Wire retrieved chunks + plan into Sonnet call [Pao] - Stream the prose; carry ENVELOPE metadata as a trailing block - do NOT wrap the visible answer in JSON [Pao] - Set max_tokens cap; Voice Card length discipline (e.g. 3-5 paragraphs unless asked to expand) [Pao] - Timeouts + bounded retries w/ backoff; graceful degradation message [Pao] - Keep Sonnet (not Haiku) [Pao] - Smoke-test 5 queries per theme [Sheena] | Pao | Wire retrieved chunks + routing plan into the Sonnet composition call. STREAM the user-facing prose directly and carry the ENVELOPE metadata {doc_ids_cited, register_used, anecdotes_deployed, signature_phrases_used} as a separate trailing block or light second pass - do NOT wrap the visible answer inside JSON that must fully arrive before rendering (that kills streaming). Set a max_tokens cap and give the Voice Card explicit length discipline (e.g. 3-5 paragraphs unless asked to expand), since output tokens drive cost/latency too. Add request timeouts + bounded retries with backoff and a graceful 'let me get back to you' degradation path. Keep Sonnet, not Haiku. | Streamed prose + trailing metadata; max_tokens + timeouts/retries in place. | Not started
W2.2 | Week 2 | Payload slimming | - Pass top-k chunks (not whole docs) [Pao] - Role-filtered enrichment per doc_id [Pao] - Directives = theme + register + Theme-A compliance only [Pao] - signature_phrases optional palette; exclude stances/decision-framework/audience/register_markers [Pao] - Make top-k + chunk budget config params [Pao] | Pao | Slim the composer payload: top-k matched chunks only (not whole docs) + role-filtered enrichment per doc_id. Directives = theme + register + Theme-A compliance; pass signature_phrases as an OPTIONAL palette ('use when natural'); EXCLUDE stances/decision_framework_signals/target_audience/register_markers (keep them diagnostic). Make top-k and chunk budget config params. | Payload = chunks + lean directives; params configurable. | Not started
W2.3 | Week 2 | Prompt-cache the static prefix | - Static prefix first (Voice Card + persona + Theme-A disclaimer) [Pao] - Variable content (chunks, query, date) last [Pao] - Confirm prefix clears the cache minimum-size threshold (or it won't cache) [Pao] - Enable Anthropic prompt caching; log cost CACHED vs UNCACHED separately [Pao] | Pao | Restructure the composer prompt so all static content (Voice Card, persona instructions, Theme-A disclaimer) is one prefix placed FIRST and variable content (chunks, query, date) LAST. Confirm the static prefix clears the cache minimum-size threshold (or it won't cache at all). Enable Anthropic prompt caching and log cost-per-query CACHED vs UNCACHED separately - pilot traffic is sporadic so the cache TTL may expire between queries; project production cost from the cached number but report the pilot's actual (likely uncached) number honestly. (Do this first in Week 2 - pure win, no quality risk.) | Prefix cached (min-size confirmed); cached vs uncached cost logged. | Not started
W2.4 | Week 2 | Build the date index | - Add dates to .md front matter [Sheena] - Build markdown date index table [Pao] - Deterministic temporal-query resolver -> doc_ids [Pao] - Remove date-stuffing from payload; pass current date only [Pao] | Both | Move dates to .md front matter, build a markdown date index, and a deterministic script resolving temporal queries ('last month','late 90s') to doc_ids. Remove date-stuffing from the Sonnet payload; pass only the current date for phrasing. | Temporal queries resolve via index; payload de-bloated. | Not started
W2.5 | Week 2 | Threshold + theme-as-control-signal | - Out-of-scope threshold + graceful fallback message [Pao] - Theme score selects register block + Theme-A disclaimer template [Pao] - Sonnet is told the theme (does not infer) [Pao] - Confirm disclaimer wording with counsel / Ma'am Ray [Sheena] - Verify disclaimer present on all Theme-A responses [Sheena] | Both | Implement the out-of-scope threshold + graceful fallback. Make the deterministic theme score SELECT the register instruction block and the Theme-A legal disclaimer template (education/opinion, never advice) - Sonnet is told the theme, not inferring it. Ensure every Theme-A response carries the disclaimer. | Out-of-scope handled; Theme-A disclaimer deterministic + approved. | Not started
W2.6 | Week 2 | Expand-on-demand fallback (gated) | - Detect weak retrieval (low fusion score / missing-context) [Pao] - Fetch fuller doc for the doc_id; recompose - cap to a SINGLE retry [Pao] - Log fire-rate; treat as a release GATE (fix upstream if > ~10%) [Pao] | Pao | Add a second-pass fallback: if retrieved chunks are insufficient (low fusion score or composer signals missing context), fetch the fuller document for the doc_id and recompose - capped to a SINGLE retry (the second call ingests a larger document and doubles the most expensive stage). Log the fire-rate and treat it as a release GATE, not just a metric: if it exceeds ~10%, the fix is upstream (better chunking or a slightly wider initial top-k), not more fallbacks. | Single-retry fallback; fire-rate logged and gated (< ~10%). | Not started
W3.1 | Week 3 | Build/extend the eval set | - Extend 49-row smoke test to a fixed pilot eval set [Sheena] - Cover grounding, AI-governance, out-of-scope, temporal, Theme-A [Sheena] - Add expected doc_ids/labels per item [Sheena] - Version-control eval_set.jsonl [Pao] | Both | Extend the 49-row smoke test into a fixed pilot eval set covering grounding-fidelity Q&A, the AI-governance retrieval case, out-of-scope queries, temporal queries, and Theme-A compliance. Add expected doc_ids/labels and version-control as eval_set.jsonl. | Versioned eval set covering all case types. | Not started
W3.2 | Week 3 | Run the quality eval | - Run eval set through new pipeline [Pao] - Score grounding fidelity; fabricated citations =0 [Pao] - Check register_used vs expected; disclaimer present [Pao] - Review diffs; categorise misses (retrieval vs composition) [Sheena] | Both | Run the eval set through the new pipeline. Score grounding fidelity, count fabricated citations (target 0), check register_used vs expected, and verify Theme-A disclaimer presence. Output a scored report + per-question diffs. | Quality scores vs target; fabrications=0; misses categorised. | Not started
W3.3 | Week 3 | Latency/cost + payload sweep | - Sweep top-k + chunk budget AND output max_tokens (output tokens drive cost too) [Pao] - Record fidelity, p50/p95, TTFT, cost/query (input vs output split) [Pao] - Start top-k LOW; raise only when recall@k demands [Pao] - Identify the knee; record config (incl. max_tokens) to Pilot Metrics [Sheena] | Pao | Run a payload sweep varying top-k, chunk budget AND the output max_tokens (output tokens drive cost/latency as much as input). For each, record grounding fidelity, latency p50/p95, time-to-first-token (separately from total), and cost/query split into input vs output. Start top-k LOW and raise only when recall@k demands it. Identify the knee where cost/latency fall steeply while quality stays flat; recommend a config including the output cap. | Sweep over top-k/chunk/output-length; knee config (incl. max_tokens) recommended. | Not started
W3.4 | Week 3 | Tune fusion + thresholds + soft prior | - Tune dense/sparse RRF weight on eval set [Pao] - Tune topic-bias lambda + the weak-prior fallback threshold [Pao] - Tune out-of-scope + topic thresholds [Pao] - Measure routing accuracy (predicted theme/topic vs gold) [Pao] - Measure retrieval recall@k (gold passage in top-k) [Pao] - Confirm soft-prior beats a hard gate; re-run affected cases [Sheena] | Pao | Tune the hybrid fusion weight (dense vs sparse), the topic-bias lambda and the weak-prior fallback threshold, and the out-of-scope + topic thresholds against the eval set to maximise grounding fidelity without latency regressions. Report two diagnostics: routing accuracy (predicted theme/topic vs the gold doc's topic) and retrieval recall@k (was the gold passage in top-k). Confirm the soft-prior design holds recall@k high even when routing is imperfect - i.e. it beats a hard topic gate. Re-run affected cases and report before/after. | Tuned weights/lambda/thresholds; routing accuracy + recall@k reported; soft-prior validated vs hard gate. | Not started
W3.5 | Week 3 | Pilot report + Go/No-Go | - Results vs each criterion (quality/latency/cost/compliance) [Sheena] - Findings + risks [Sheena] - Go/No-Go recommendation for full-corpus scaling [Sheena] - Build Word doc (navy/gold palette) [Sheena] | Sheena | Synthesise the eval and latency/cost results into a pilot report: results vs each success criterion (quality, latency, cost, compliance), findings, risks, and a Go/No-Go recommendation for scaling to the full 1,000+ corpus. Build as a Word doc in the navy/gold judicial palette. | Pilot report delivered; Go/No-Go decision documented. | Not started
W3.6 | Week 3 | ADRs + scale-up plan | - ADRs: hybrid, embeddings-over-keywords, Sonnet-not-Haiku, payload slimming+caching [Sheena] - Scale-path risks: O(N) cosine -> ANN (hnswlib/FAISS); tighten soft-prior global fallback at full scale [Pao] - Scale-up: progressive-disclosure folders (per-folder CLAUDE.md + indexes) [Pao] - Corpus token-efficiency workstream outline [Pao] | Both | Write short ADRs (hybrid retrieval; embeddings-over-keywords with keywords as sparse+diagnostic; Sonnet-not-Haiku; payload slimming + prefix caching). Record scale-path risks explicitly: brute-force in-memory cosine is O(N) per query (fine at thousands, slow at 100k+) -> plan an ANN index (hnswlib/FAISS); and the soft-prior global fallback scans the full index when the prior is weak -> tighten the fallback policy at full-corpus scale. Add a scale-up outline: progressive-disclosure folder structure (per-folder CLAUDE.md + indexes) and the corpus token-efficiency workstream. | ADRs filed; scale-path risks + scale-up outline documented. | Not started
Lead key: Pao = code/implementation . Sheena = support/curation/docs . Both = shared with subtask split shown.

## Pilot Metrics
Pilot Metrics - targets + baseline in Week 1, results in Week 3
Metric | Definition | Target (set W1) | Baseline | Pilot result | Pass?
End-to-end latency p50 | Median total response time across the eval set. | [ set ] | [ ] | [ ] | [ ]
End-to-end latency p95 | 95th-percentile total response time (worst-case paths show here). | [ set ] | [ ] | [ ] | [ ]
Time-to-first-token (TTFT) | First-token latency, measured separately from total - streaming can mask slow generation. | [ set ] | [ ] | [ ] | [ ]
Per-stage latency | Time in input gate / router / retrieval / composer. | [ set ] | [ ] | [ ] | [ ]
Fabricated citations | Citations not supported by the corpus. Target = 0. | [ set ] | [ ] | [ ] | [ ]
Grounding-fidelity score | Eval-set score for answers grounded in retrieved chunks. | [ set ] | [ ] | [ ] | [ ]
In-voice register match | register_used vs expected on the eval set. | [ set ] | [ ] | [ ] | [ ]
AI-governance retrieval | Whether the known retrieval miss is now surfaced. | [ set ] | [ ] | [ ] | [ ]
Out-of-scope handling | Off-taxonomy queries correctly thresholded + declined. | [ set ] | [ ] | [ ] | [ ]
Routing accuracy | Predicted theme/topic vs the gold doc's topic on the eval set. | [ set ] | [ ] | [ ] | [ ]
Retrieval recall@k | Share of eval queries with the gold passage in top-k (soft-prior should hold this high even when routing errs). | [ set ] | [ ] | [ ] | [ ]
Cost per query | Avg API cost per response - log INPUT vs OUTPUT and CACHED vs UNCACHED; should fall vs baseline. | [ set ] | [ ] | [ ] | [ ]
Output tokens per answer | Average answer length in tokens - drives cost/latency regardless of payload size. | [ set ] | [ ] | [ ] | [ ]
Theme-A disclaimer present | Share of law-themed responses with the disclaimer. Target = 100%. | [ set ] | [ ] | [ ] | [ ]
Payload knee config | top-k / chunk budget / max_tokens where quality is flat but cost/latency drop. | [ set ] | [ ] | [ ] | [ ]
Dense/sparse fusion weight | Tuned RRF weighting + topic-bias lambda. | [ set ] | [ ] | [ ] | [ ]
Register-classifier accuracy | Deterministic register vs hand labels. | [ set ] | [ ] | [ ] | [ ]
Prefix cache hit rate | Share of composer calls hitting the cached prefix. | [ set ] | [ ] | [ ] | [ ]
Expand-on-demand fire rate | Share of queries needing the whole-doc fallback. Release GATE: fix upstream if > ~10%. | [ set ] | [ ] | [ ] | [ ]
Blue cells are inputs for the team to fill in.