## Pilot Plan
CJP AI Persona — Pilot Execution Plan (3 weeks, 2-person)
<100-doc pilot . Pao leads implementation (Claude Code) . Sheena supports (prep, curation, eval, docs)
OBJECTIVE
Prove, on a curated subset of fewer than 100 documents, that the hybrid retrieval + Sonnet composition pipeline produces high-fidelity, in-voice CJP responses with acceptable latency and an improving cost-per-query, before scaling to the full 1,000+ document corpus.
TEAM & WORKING MODEL
Pao - implementation lead | Owns the code path via Claude Code: repo, chunking, embeddings, sparse arm, fusion, routing, composer, payload slimming, caching, evals.
Sheena - support | Corpus prep & normalisation QA, pilot doc-set curation, exemplars, eval-set authoring, output verification, metrics recording, document deliverables (Cowork).
Working pattern | Two parallel tracks with hand-offs: Sheena prepares/curates and verifies what Pao builds; Pao consumes Sheena's frozen inputs. Respect the Depends order.
SCOPE SPLIT (full corpus vs pilot subset)
Taxonomy = full corpus | The topic map, clustering, centroids and independence check are built on the FULL ~1,000-doc corpus, so topic structure, orphaned content and empty topics are seen accurately - a 100-doc slice would distort them (a topic may look orphaned at 100 but be well-populated at 1,000).
Pilot run/eval = <100 | The pipeline is RUN and EVALUATED on the curated <100 subset, tagged against the full taxonomy. Small = fast to iterate and hand-checkable for grounding/fabrication. Composer latency & cost are per-query, independent of corpus size.
ARCHITECTURE AT A GLANCE
Offline build | Normalised UTF-8 corpus; heading-aware chunks + doc store keyed by doc_id; dense embeddings (bge-large @1024d, local); BM25 sparse index + curated keyword/entity dictionary; topic centroids; date index; Voice Card.
Runtime - code | Query embed -> centroid scoring -> theme/topic routing; hybrid fusion (dense + sparse, RRF) -> top-k chunks; deterministic register + disclaimer selection. No LLM in this path.
Retrieval principle | Topics BIAS retrieval (a soft prior + register/disclaimer driver); PASSAGES decide (passage-level ranking); the sparse arm rescues exact identifiers. Topics never hard-gate retrieval - a routing error must not hide the right passage.
Runtime - Sonnet | Composition only: slim payload (top-k chunks + lean directives + cached Voice Card prefix) -> ENVELOPE. Streamed.
Embedding model | bge-large-en-v1.5 local @1024d (strong recall, resident, zero per-call cost, data stays on-prem). Benchmarked alternatives in W3.4: MiniLM (lighter/faster) and OpenAI text-embedding-3 (hosted, stronger but network hot-path + per-call cost + data leaves infra). Same model for docs, queries, centroids.
Biggest cost lever | Payload slimming (chunks not whole docs) + prompt-caching the static prefix - not the embedding model or the router.
LATENCY / COST GUARDRAILS (from architecture review)
Measure p95 & TTFT | Track p95 and time-to-first-token, not just medians - the worst-case paths (fallback double-call, cold start, cache miss, API variance) inflate p95, not the median you look at first.
Output side too | Output tokens drive cost/latency as much as input: cap max_tokens, give the Voice Card length discipline, and stream prose (don't wrap the visible answer in JSON).
Treat as gates | Expand-on-demand fire-rate (target < ~10%) and cache-hit rate are release gates; default top-k starts low and rises only when recall@k demands it.
Retrieval cutoff | Dynamic relevance cutoff (keep chunks with score >= tau*top_score) bounded by min_k/max_k - adapts chunk count to relevance, not a fixed top-k.
Config & voice | All knobs in one config.py (tau, min_k/max_k, max_tokens, lambda, thresholds). Voice front-end: stream -> sentence-chunk -> TTS; optional in-voice Haiku filler; NO raw reasoning-trace narration.
PHASE SUMMARY (3 weeks)
Week | Theme & focus
Week 1 | Foundation + hybrid retrieval (two weeks condensed) - stabilise + unified config.py, normalise corpus, freeze the <100 pilot subset, chunk + embed, sparse arm + keyword dictionary, taxonomy on the FULL corpus, fusion + code routing (dynamic relevance cutoff), latency baseline, decisions memo.
Week 2 | Composition, payload slimming & guardrails - Sonnet composer + ENVELOPE, slim payload, prefix caching, date index, threshold + theme-as-control-signal disclaimer, expand-on-demand, voice/TTS front-end.
Week 3 | Evaluate, tune & decide - eval set, quality + latency/cost evals, payload sweep to the knee, fusion/threshold tuning, pilot report + Go/No-Go, ADRs.
NOTE ON WEEK 1 LOAD
Week 1 intentionally carries two weeks of build scope. It is feasible only because the two tracks run in parallel and Claude Code accelerates implementation. The full-corpus taxonomy (W1.7) is foundational and should not slip; if pressure mounts, the safest items to push into Week 2 are the centroid independence REVIEW (the merge/sharpen pass within W1.7) and the register classifier (part of W1.8) - both refinements, not core-path blockers.

## Weekly Tasks
Weekly Task Tracker - CJP AI Persona Pilot (<100 docs) . 3-week, 2-person playbook (Pao + Sheena)
Pao = implementation (Claude Code). Sheena = support: prep, curation, verification, docs (Cowork). Subtasks tagged [Pao]/[Sheena]. Update Status as you go.
ID | Week | Task | Subtasks (with owner) | Lead | Claude Code / Cowork prompt (paste-ready) | Result / acceptance | Status
W1.1 | Week 1 | Stabilise codebase + unified config.py | - Audit branches; consolidate to one clean branch; resolve conflicts [Pao] - Tag baseline 'pilot-baseline'; set up pilot working dir [Pao] - Create unified config.py: tau, min_k/max_k, max_tokens, fusion lambda, thresholds, model IDs, timeouts [Pao] - Confirm end-to-end run; document env/setup steps [Sheena] | Pao | Open the repo (Supervaise-Reachy-Mini-Project). Audit branches, consolidate to one clean working branch, resolve conflicts, tag 'pilot-baseline', and confirm an end-to-end run. Create a SINGLE config.py (or a YAML it loads) holding every tunable knob - relevance threshold tau, min_k/max_k, max_tokens, fusion weight lambda, out-of-scope/topic thresholds, model IDs, timeouts - so the W3.3 sweep varies config, not code. Output a short changelog + env/setup steps. | Single clean branch; baseline tagged (pilot-baseline = CODE/CONFIG baseline, pre-W1.7 rebuild & pre-W1.8 build); config.py centralises all knobs (46). Regression run passed; live e2e DEFERRED to W1.11 arch-baseline. | Done
W1.2 | Week 1 | Normalise & prep the corpus | - Write normalisation script: mojibake->UTF-8, quotes/dashes [Pao] - Safely parse JSON-list fields; casefold/strip keywords [Pao] - Re-save utf-8-sig, ensure_ascii=False [Pao] - Run on all curated CSVs; QA rows changed; spot-check 10 docs [Sheena] - Log unparseable fields for follow-up [Sheena] | Pao | Write/run a normalisation script for the curated CSVs (e.g. cjp_columns_curated.csv): fix cp1252 mojibake (0x97 em-dash, 0x91-0x94 smart quotes, 0x9d) to UTF-8, normalise curly quotes/dashes to ASCII, safely parse JSON-list fields (Keyword/s, primary_topics, sub_topics, signature_phrases, entities), casefold/strip keyword tokens, re-save as utf-8-sig with ensure_ascii=False, and report rows changed + unparseable fields. | Clean UTF-8 corpus; mojibake=0; QA report; issues logged. | Not started
W1.3 | Week 1 | Freeze the pilot/eval subset (v4 ALLOWLIST, <100) | - Re-freeze as v4: balanced 95 docs (19/theme), <100 cap restored; supersedes v3/v2/v1 (all retained) [Sheena] - v4 is an EVAL-TIME ALLOWLIST of doc_ids (consumed at W1.5/W3) - it does NOT drive chunking [Sheena] - Re-derive forced lists from full corpus: fix CA060 (indigents != indigenous) + SD035 (not climate); expand under-inclusive AI-governance set; keep all forced docs [Sheena] - Relabel: "balanced for per-theme eval power" (NOT "representative"); strata = coarse curated-theme (ADR-0011 letter), to be re-tagged at W1.7; biography GC### = ID-convention artifact [Sheena] - Output v4 frozen list + coverage table + forced-inclusions (with keyword evidence) + selection notes [Sheena] | Sheena | Re-freeze the pilot subset as v4: a balanced 95-doc (19/theme) EVAL-TIME ALLOWLIST of doc_ids - NOT the chunking input (W1.4 chunks the FULL corpus). Restore the <100 cap (v3 broke nothing but v2 did); retain all forced docs but RE-DERIVE the AI-governance + orphaned-topic lists from the full normalised corpus (operationalise: Keyword/s field, casefold at tally, strip person-name tokens, orphaned <=2 docs). Fix the CA060 (indigents, not "indigenous peoples") and SD035 (FLP Scholars/COVID, not "climate") mislabels with keyword evidence; expand the under-inclusive AI set (CE018/CA095/CE019/...). Drop the "representative" claim - label it "balanced for per-theme eval power" and state the corpus is ~55% theme A. Relabel strata as coarse curated-theme (ADR-0011 ID letter, NOT the W1.7 taxonomy, which does not exist yet); reword the biography note as an ID-convention artifact. Read corpus from the confirmed data/csv/*_curated_normalized.xlsx. Do NOT modify v1/v2/v3. If re-derived forced docs push a theme past 19, FLAG for a PM call - do not silently drop a forced doc. Output: pilot_subset_frozen_v4.csv, coverage_table_v4.csv, forced_inclusions_v4.csv (with keyword evidence), selection_notes_v4.txt. | Frozen v4 ALLOWLIST (<100, expect 95 balanced) + coverage table handed to Pao. Forced lists re-derived (CA060/SD035 corrected, AI set expanded); "representative" claim removed; theme/biography framing fixed; v1/v2/v3 retained. | Not started
W1.4 | Week 1 | Corpus prep + FULL-corpus chunking + doc store (pinned) | - Regenerate the corpus/ markdown tree FROM the four data/csv/*_curated_normalized.xlsx (repoint generate_corpus_files.py off the stale 80-doc CSVs) [Pao] - PIN the corpus: track xlsx in git + corpus_snapshot.json (per-file sha256 + per-doc row hash) + verify_pin.py that fails on drift [Pao] - Heading-aware chunking (~200-400 tokens, small overlap) over the FULL ~1,089-doc corpus; all knobs from config.py [Pao] - Build doc store (chunk_id -> doc_id, metadata + anecdotes) + chunk index; built ONCE, stable across subset re-freezes [Pao] - Verify: all 95 pilot-allowlist docs resolve to chunks; boundaries + anecdotes verified [Pao] | Pao | Chunk the FULL ~1,089-doc corpus (architecture decision: subset is an eval-time allowlist, NOT the chunk input). FIRST regenerate the corpus/ markdown tree from the confirmed data/csv/*_curated_normalized.xlsx - the existing tree is built by generate_corpus_files.py from the STALE 80-doc tracked CSVs (no books), so 89/95 pilot docs are currently missing; repoint that script to the xlsx and regenerate all ~1,089 docs (doc_id = padded Article Code; entities stays a JSON object). THEN pin the corpus so "frozen" is verifiable: track the four xlsx in git (or commit CSV exports) and write corpus_snapshot.json with per-file sha256 + per-doc row_sha256 (canonical 15-field serialization) + a producer/date header; add scripts/verify_pin.py that recomputes both and exits nonzero on drift. THEN heading-aware chunk (~200-400 tokens, small overlap, knobs from config.py) the full corpus, retaining anecdotes and respecting section boundaries; build the doc store + chunk index ONCE. Verify: full corpus chunked; all 95 pilot-allowlist doc_ids resolve to chunks (the missing-89 problem is gone); boundary + anecdote spot-checks on a sample including several of the 95; verify_pin passes. Report corpus count (+ the 1,059-vs-1,089 discrepancy with the real number), chunk stats, and the 95-doc resolution check. | Full corpus regenerated from xlsx + chunked; doc store + chunk index built (once, stable); anecdotes retained; boundaries verified; ALL 95 allowlist docs resolve; corpus PINNED (snapshot + verify_pin PASSES). Subset is an allowlist applied at W1.5/W3, not here. | Not started
W1.5 | Week 1 | Embed the pilot subset (runtime index) | - Load chosen model: bge-large-en-v1.5 @1024d (local, strong, resident) - swappable via config.py [Pao] - Load model ONCE at service start (resident) - never per-request, to avoid cold-start spikes [Pao] - Embed the <100 subset chunks; numpy float32 matrix + persist [Pao] - Same model/dim for queries, centroids & full-corpus taxonomy (W1.7) [Pao] - Apply search_query/search_document input types (bge supports them) [Pao] | Pao | Embed the <100 pilot-subset chunks with bge-large-en-v1.5 @1024d (LOCAL, resident; model id lives in config.py so it stays swappable - MiniLM and OpenAI text-embedding-3 are the alternatives benchmarked in W3.4). Local-strong is chosen over MiniLM (quality) and over hosted GPT/OpenAI (keeps the query off the network hot path, no per-call cost, corpus/queries never leave our infra). Load the model ONCE at service start and keep it resident to avoid cold-start spikes. Store vectors in an in-memory numpy float32 matrix indexed by chunk_id, persisted to .npy + json. Use the SAME model/dim for queries, centroids, and the full-corpus taxonomy (W1.7). Apply bge search_query/search_document input types. | Pilot-subset index embedded with bge-large (local, resident), persisted and queryable; model id config-driven. | Not started
W1.6 | Week 1 | Build the sparse arm (BM25) | - BM25 index over full chunk text [Pao] - Load curated keywords+entities as atomic-phrase dictionary [Pao] - Keep multi-word keywords as single terms (no whitespace split) [Pao] - Expose sparse_score(query) -> ranked chunk_ids [Pao] - KEEP BM25 regardless of dense model: no embedding matches exact identifiers (complementary, not redundant) [Pao] | Pao | Build a BM25 index over full chunk text. Load the normalised curated Keyword/s + entities as an atomic-phrase boost dictionary - treat each multi-word keyword as a single term (do NOT whitespace-tokenise; 91% are multi-word). Expose sparse_score(query) returning ranked chunk_ids. Keep the sparse arm regardless of which dense embedding is used (MiniLM/bge/OpenAI) - exact-identifier matching is complementary to semantic recall, not redundant. | BM25 + keyword dictionary returns ranked chunks. | Not started
W1.7 | Week 1 | Regenerate topic map FROM SCRATCH on FULL corpus (new centroid model) + tag subset | - Rebuild centroids from scratch under the new dimensional model: centroid = mean(label + description + signature_phrases + exemplar chunks) [Both] - Embed the full ~1,000-doc corpus offline (bge-large, local) [Pao] - Re-run independence check (cosine > 0.85 merge) + coverage/orphaned-content analysis; do NOT carry over or incrementally expand the old 35-topic map [Both] - Tag the frozen <100 pilot subset against the regenerated centroids (1-3 topics, primary+secondary) [Pao] - All topic-model params read from config.py (TOPIC_MERGE_COSINE, MAX_TOPIC_TAGS, CENTROID_SOURCE_FIELDS) [Pao] | Both | Regenerate the topic map FROM SCRATCH on the FULL ~1,000-doc corpus under the new dimensional/centroid model - do NOT start from or expand the existing 35-topic map (it is stale: its own health check flags independence violations above the 0.85 bar). Each topic centroid = mean(label + description + signature_phrases + exemplar chunks). Embed the full corpus offline with bge-large-en-v1.5 (the same local model as W1.5). Re-run the independence check (merge pairs with cosine > TOPIC_MERGE_COSINE) and a coverage analysis (flag orphaned content with no matching topic). Then tag the frozen <100 pilot subset against the regenerated centroids (primary + secondary, up to MAX_TOPIC_TAGS). Read every topic-model knob from config.py. Report: topic count, merged pairs, coverage gaps, and the subset tagging summary. | Topic map REGENERATED from scratch (not incrementally expanded); independence + coverage re-analysed; orphaned content flagged; pilot subset tagged; fully config-driven. | Not started
W1.8 | Week 1 | BUILD the new retrieval architecture - Haiku-out, centroid + RRF hybrid, soft prior | - Remove the Haiku router entirely from the serial path; delete the pre-retrieval LLM round-trip [Pao] - Deterministic code router: query embed -> centroid scoring -> softmax + out-of-scope gate -> theme/topic select as SOFT PRIOR, not a hard gate [Pao] - Hybrid fusion: bge-large dense + BM25 sparse via RRF -> ranked passages [Pao] - Soft-prior scoring: score = passage_sim + lambda*topic_affinity; global fallback when prior weak [Pao] - Dynamic cutoff: keep chunks where score >= tau*top_score, bounded by min_k/max_k [Pao] - Deterministic selection: register/theme cues, Theme-A disclaimer template, date resolution [Pao] - Every knob from config.py (no new literals); deprecate/remove vestigial ROUTER_MODEL_ID [Pao] | Pao | BUILD the new retrieval architecture (this is a BUILD, not a tune - the architecture is design-only today and the live path is still Haiku->Sonnet). Branch off the current pilot branch. Read all knobs from config.py; introduce NO new literals; do NOT tune weights/thresholds (that is W3.4 - use config defaults). Preconditions (confirm they exist, else stop and report): dense index (W1.5), BM25 sparse (W1.6), regenerated centroids (W1.7). 1) REMOVE HAIKU: delete the pre-retrieval Haiku call; after this ZERO LLM round-trips before composition - prove via per-stage timing; mark ROUTER_MODEL_ID deprecated. 2) CODE ROUTER (soft prior): query embed (resident bge-large, no cold start) -> centroid cosine -> softmax -> relevance vector; OUT_OF_SCOPE_THRESHOLD decides in/out; theme selection BIASES, never gates; weak prior falls through to global retrieval. 3) HYBRID RRF: dense + BM25 fused by RRF (RRF_K); apply score = passage_sim + LAMBDA*topic_affinity with global fallback (guard the orphaned-content failure mode). 4) DYNAMIC CUTOFF: keep score >= TAU*top_score, bounded MIN_K/MAX_K. 5) DETERMINISTIC SELECTION: register/theme cues, deterministic Theme-A disclaimer, date resolution; assemble slim top-k payload (chunks, not whole docs). 6) e2e on the <100 subset at config defaults (needs ANTHROPIC_API_KEY); paste command + grounded sample + per-stage timing showing no pre-composition LLM call. Flag inconsistencies; do not silently fix outside scope. | Haiku fully removed (per-stage log shows ZERO LLM round-trips before composition). Centroid scoring + RRF passage ranking live; soft prior + global fallback + dynamic cutoff all config-driven. Deterministic theme/date selection. Runs e2e on the <100 subset at config defaults. NO tuning here (that is W3.4). | Not started
W1.9 | Week 1 | Latency logging + baseline | - Per-stage timing (input gate->router->retrieval->composer) [Pao] - Capture time-to-first-token (TTFT) separately from total [Pao] - JSON-lines logs + p50/p95 summary script (report p95, not just median) [Pao] - Warm the model/service before measuring (steady-state, not cold) [Pao] - Run baseline on current pipeline over draft queries [Pao] - Record baseline latency/TTFT/cost/quality to Pilot Metrics [Sheena] | Both | Add per-stage timing (ASR if present -> input gate -> router -> retrieval -> composer) emitting JSON-lines logs, plus a script summarising p50/p95 per stage. Capture time-to-first-token separately from total latency and report p95 (not just median). Warm the model/service before the baseline run so you measure steady-state, not cold-start. Run the frozen pilot set through the current pipeline and write baseline latency (e2e + per-stage + TTFT), cost/query and quality to baseline.json. | Per-stage + TTFT logging live; warmed baseline (p50/p95) recorded. | Not started
W1.10 | Week 1 | Lock decisions memo | - Record embedding model, store, hybrid architecture [Sheena] - Record routing + theme-as-control-signal decisions [Sheena] - Set latency/quality/cost targets in Pilot Metrics [Sheena] - Circulate for sign-off [Sheena] | Sheena | Draft a one-page Week-1 Decisions memo: embedding model (DEFAULT bge-large-en-v1.5 local @1024d; MiniLM and OpenAI text-embedding-3 are benchmarked alternatives, final call from the W3.4 bake-off), in-memory numpy retrieval, hybrid dense+sparse(BM25)+keyword dictionary, centroid topic dimensions, deterministic code routing, theme-as-control-signal, and latency/quality/cost targets. One decision per row with rationale + owner. | Decisions memo signed off; targets entered. | Not started
W1.11 | Week 1 | arch-baseline checkpoint - first new-arch e2e + latency/cost anchor | - Run the first full pilot e2e on the <100 subset through the NEW architecture [Pao] - Capture per-stage latency p50/p95 + TTFT (+ TTFA if voice path wired) [Pao] - Verify Haiku absent from the path; record cached vs uncached compose cost if caching present [Pao] - Tag arch-baseline (annotated) as the OFFICIAL W3.3 sweep anchor - NOT pilot-baseline [Pao] - Enter the numbers into metrics sheet / decisions memo [Sheena] | Pao | Run the first real end-to-end of the new architecture on the <100 pilot subset (needs ANTHROPIC_API_KEY). Capture per-stage latency p50/p95 and TTFT (and TTFA if the voice front-end is wired). Verify empirically that Haiku is absent from the path (no LLM round-trip before composition). If prompt caching is in place, record cached vs uncached compose cost. Then create an annotated tag arch-baseline and document it as the OFFICIAL latency/cost comparison anchor for the W3.3 sweep - pilot-baseline must NOT be used (it is the old Haiku-in-path, un-slimmed-payload baseline). Hand the numbers to Sheena for the metrics sheet / decisions memo. | New-arch e2e returns a grounded answer; per-stage + TTFT baseline recorded; Haiku-absence verified; arch-baseline tag created and designated the W3.3 comparison anchor. | Not started
W2.1 | Week 2 | Sonnet composer + ENVELOPE (guardrails) | - Wire retrieved chunks + plan into Sonnet call [Pao] - Stream the prose; carry ENVELOPE metadata as a trailing block - do NOT wrap the visible answer in JSON [Pao] - Set max_tokens cap; Voice Card length discipline (e.g. 3-5 paragraphs unless asked to expand) [Pao] - Timeouts + bounded retries w/ backoff; graceful degradation message [Pao] - Keep Sonnet (not Haiku) [Pao] - Smoke-test 5 queries per theme [Sheena] | Pao | Wire retrieved chunks + routing plan into the Sonnet composition call. STREAM the user-facing prose directly and carry the ENVELOPE metadata {doc_ids_cited, register_used, anecdotes_deployed, signature_phrases_used} as a separate trailing block or light second pass - do NOT wrap the visible answer inside JSON that must fully arrive before rendering (that kills streaming). Set a max_tokens cap and give the Voice Card explicit length discipline (e.g. 3-5 paragraphs unless asked to expand), since output tokens drive cost/latency too. Add request timeouts + bounded retries with backoff and a graceful 'let me get back to you' degradation path. Keep Sonnet, not Haiku. | Streamed prose + trailing metadata; max_tokens + timeouts/retries in place. | Not started
W2.2 | Week 2 | Payload slimming | - Pass top-k chunks (not whole docs) [Pao] - Role-filtered enrichment per doc_id [Pao] - Directives = theme + register + Theme-A compliance only [Pao] - signature_phrases optional palette; exclude stances/decision-framework/audience/register_markers [Pao] - Make top-k + chunk budget config params [Pao] | Pao | Slim the composer payload: top-k matched chunks only (not whole docs) + role-filtered enrichment per doc_id. Directives = theme + register + Theme-A compliance; pass signature_phrases as an OPTIONAL palette ('use when natural'); EXCLUDE stances/decision_framework_signals/target_audience/register_markers (keep them diagnostic). Make top-k and chunk budget config params. | Payload = chunks + lean directives; params configurable. | Not started
W2.3 | Week 2 | Prompt-cache the static prefix | - Static prefix first (Voice Card + persona + Theme-A disclaimer) [Pao] - Variable content (chunks, query, date) last [Pao] - Confirm prefix clears the cache minimum-size threshold (or it won't cache) [Pao] - Enable Anthropic prompt caching; log cost CACHED vs UNCACHED separately [Pao] | Pao | Restructure the composer prompt so all static content (Voice Card, persona instructions, Theme-A disclaimer) is one prefix placed FIRST and variable content (chunks, query, date) LAST. Confirm the static prefix clears the cache minimum-size threshold (or it won't cache at all). Enable Anthropic prompt caching and log cost-per-query CACHED vs UNCACHED separately - pilot traffic is sporadic so the cache TTL may expire between queries; project production cost from the cached number but report the pilot's actual (likely uncached) number honestly. (Do this first in Week 2 - pure win, no quality risk.) | Prefix cached (min-size confirmed); cached vs uncached cost logged. | Not started
W2.4 | Week 2 | Build the date index | - Add dates to .md front matter [Sheena] - Build markdown date index table [Pao] - Deterministic temporal-query resolver -> doc_ids [Pao] - Remove date-stuffing from payload; pass current date only [Pao] | Both | Move dates to .md front matter, build a markdown date index, and a deterministic script resolving temporal queries ('last month','late 90s') to doc_ids. Remove date-stuffing from the Sonnet payload; pass only the current date for phrasing. | Temporal queries resolve via index; payload de-bloated. | Not started
W2.5 | Week 2 | Threshold + theme-as-control-signal | - Out-of-scope threshold + graceful fallback message [Pao] - Theme score selects register block + Theme-A disclaimer template [Pao] - Sonnet is told the theme (does not infer) [Pao] - Confirm disclaimer wording with counsel / Ma'am Ray [Sheena] - Verify disclaimer present on all Theme-A responses [Sheena] | Both | Implement the out-of-scope threshold + graceful fallback. Make the deterministic theme score SELECT the register instruction block and the Theme-A legal disclaimer template (education/opinion, never advice) - Sonnet is told the theme, not inferring it. Ensure every Theme-A response carries the disclaimer. | Out-of-scope handled; Theme-A disclaimer deterministic + approved. | Not started
W2.6 | Week 2 | Expand-on-demand fallback (gated) | - Detect weak retrieval (low fusion score / missing-context) [Pao] - Fetch fuller doc for the doc_id; recompose - cap to a SINGLE retry [Pao] - Log fire-rate; treat as a release GATE (fix upstream if > ~10%) [Pao] | Pao | Add a second-pass fallback: if retrieved chunks are insufficient (low fusion score or composer signals missing context), fetch the fuller document for the doc_id and recompose - capped to a SINGLE retry (the second call ingests a larger document and doubles the most expensive stage). Log the fire-rate and treat it as a release GATE, not just a metric: if it exceeds ~10%, the fix is upstream (better chunking or a slightly wider initial top-k), not more fallbacks. | Single-retry fallback; fire-rate logged and gated (< ~10%). | Not started
W2.7 | Week 2 | Voice/TTS front-end (stream -> TTS) | - Approach 3 backbone: stream Sonnet output; chunk at SENTENCE/clause boundaries; feed TTS incrementally [Pao] - Confirm TTS consumes incrementally (else the streaming gain is lost) [Pao] - Optional: in-voice Haiku filler if a pre-generation pause remains (Approach 1) [Pao] - Simpler alt first: tighter max_tokens to cut generation time [Pao] - DECISION: NO raw reasoning-trace narration (Approach 2) - off-voice + leakage risk [Pao] - Measure time-to-first-audio (TTFA) [Sheena] | Pao | Build the voice front-end after the composer. BACKBONE (Approach 3): stream Sonnet's output and feed TTS incrementally, chunked at sentence/clause boundaries (never mid-token); confirm the TTS engine accepts incremental input or the streaming gain is lost. Keep the prose unwrapped (no JSON). ENHANCEMENT (Approach 1, optional): only if a pre-first-token pause remains, play a short IN-VOICE Haiku-composed filler while Sonnet works - the simpler first move is a tighter max_tokens. DECISION: do NOT narrate raw reasoning traces (Approach 2) - they are off-persona and leak deliberation. Measure time-to-first-audio. | Streaming TTS with sentence-boundary chunking; TTFA measured; no raw-trace narration. | Not started
W3.1 | Week 3 | Build/extend the eval set | - Extend 49-row smoke test to a fixed pilot eval set [Sheena] - Cover grounding, AI-governance, out-of-scope, temporal, Theme-A [Sheena] - Add expected doc_ids/labels per item [Sheena] - Version-control eval_set.jsonl [Pao] | Both | Extend the 49-row smoke test into a fixed pilot eval set covering grounding-fidelity Q&A, the AI-governance retrieval case, out-of-scope queries, temporal queries, and Theme-A compliance. Add expected doc_ids/labels and version-control as eval_set.jsonl. | Versioned eval set covering all case types. | Not started
W3.2 | Week 3 | Run the quality eval | - Run eval set through new pipeline [Pao] - Score grounding fidelity; fabricated citations =0 [Pao] - Check register_used vs expected; disclaimer present [Pao] - Review diffs; categorise misses (retrieval vs composition) [Sheena] | Both | Run the eval set through the new pipeline. Score grounding fidelity, count fabricated citations (target 0), check register_used vs expected, and verify Theme-A disclaimer presence. Output a scored report + per-question diffs. | Quality scores vs target; fabrications=0; misses categorised. | Not started
W3.3 | Week 3 | Latency/cost + payload sweep | - Sweep relevance threshold tau (+ min_k/max_k), chunk budget AND output max_tokens [Pao] - Record fidelity, p50/p95, TTFT/TTFA, cost/query (input vs output), chunks/query [Pao] - Start strict (high tau / low max_k); relax only when recall@k demands [Pao] - Identify the knee; record config (tau, min_k/max_k, max_tokens) to Pilot Metrics [Sheena] | Pao | Run a payload sweep varying the relevance threshold tau (with min_k/max_k bounds), the chunk budget, AND the output max_tokens (output tokens drive cost/latency as much as input). For each, record grounding fidelity, latency p50/p95, time-to-first-token/audio, cost/query split input vs output, and the avg chunks admitted per query. Start strict (higher tau, lower max_k) and relax only when recall@k demands it. Identify the knee where cost/latency fall steeply while quality stays flat; recommend a config (tau, min_k/max_k, max_tokens). | Sweep over tau/min_k/max_k/chunk/output; knee config recommended. | Not started
W3.4 | Week 3 | Tune fusion + thresholds + soft prior | - Tune dense/sparse RRF weight on eval set [Pao] - Tune topic-bias lambda + the weak-prior fallback threshold [Pao] - Tune out-of-scope + topic thresholds [Pao] - Measure routing accuracy (predicted theme/topic vs gold) [Pao] - Measure retrieval recall@k (gold passage in top-k) [Pao] - Confirm soft-prior beats a hard gate; re-run affected cases [Sheena] - Embedding bake-off: MiniLM vs bge-large vs OpenAI text-embedding-3 on recall@k + grounding (same pilot set) [Pao] | Pao | Tune the hybrid fusion weight (dense vs sparse), the topic-bias lambda and the weak-prior fallback threshold, and the out-of-scope + topic thresholds against the eval set to maximise grounding fidelity without latency regressions. Report two diagnostics: routing accuracy (predicted theme/topic vs the gold doc's topic) and retrieval recall@k (was the gold passage in top-k). Confirm the soft-prior design holds recall@k high even when routing is imperfect - i.e. it beats a hard topic gate. Re-run affected cases and report before/after. Also run an EMBEDDING BAKE-OFF: re-embed the pilot set with MiniLM, bge-large, and OpenAI text-embedding-3, and compare recall@k and grounding fidelity on the same eval; recommend the dense model on evidence (default stays bge-large unless a gap justifies hosted, weighed against its latency/cost/data-governance cost). | Tuned weights/lambda/thresholds; routing accuracy + recall@k reported; soft-prior validated vs hard gate. Embedding bake-off recommends the dense model on evidence. | Not started
W3.5 | Week 3 | Pilot report + Go/No-Go | - Results vs each criterion (quality/latency/cost/compliance) [Sheena] - Findings + risks [Sheena] - Go/No-Go recommendation for full-corpus scaling [Sheena] - Build Word doc (navy/gold palette) [Sheena] | Sheena | Synthesise the eval and latency/cost results into a pilot report: results vs each success criterion (quality, latency, cost, compliance), findings, risks, and a Go/No-Go recommendation for scaling to the full 1,000+ corpus. Build as a Word doc in the navy/gold judicial palette. | Pilot report delivered; Go/No-Go decision documented. | Not started
W3.6 | Week 3 | ADRs + scale-up plan | - ADRs: hybrid, dense-embedding-choice (bge-large local; bake-off), embeddings-over-keywords, Sonnet-not-Haiku, payload slimming+caching [Sheena] - Scale-path risks: O(N) cosine -> ANN (hnswlib/FAISS); tighten soft-prior global fallback at full scale [Pao] - Scale-up: progressive-disclosure folders (per-folder CLAUDE.md + indexes) [Pao] - Corpus token-efficiency workstream outline [Pao] | Both | Write short ADRs (hybrid retrieval; embeddings-over-keywords with keywords as sparse+diagnostic; Sonnet-not-Haiku; payload slimming + prefix caching). Record scale-path risks explicitly: brute-force in-memory cosine is O(N) per query (fine at thousands, slow at 100k+) -> plan an ANN index (hnswlib/FAISS); and the soft-prior global fallback scans the full index when the prior is weak -> tighten the fallback policy at full-corpus scale. Add a scale-up outline: progressive-disclosure folder structure (per-folder CLAUDE.md + indexes) and the corpus token-efficiency workstream. Add a dense-embedding-choice ADR: why local bge-large over MiniLM (quality) and over hosted GPT/OpenAI (latency hot-path, per-call cost, and data-governance - corpus/queries stay on-prem), backed by the W3.4 bake-off numbers. | ADRs filed; scale-path risks + scale-up outline documented. Incl. dense-embedding-choice ADR. | Not started
Lead key: Pao = code/implementation . Sheena = support/curation/docs . Both = shared with subtask split shown.
Note on F5: Note (post-run): suggested base 'feat/topic-map-coverage' did NOT exist; base chosen on evidence = pre-wake-word-integration @07a8b8d. The 'locked new architecture' (centroids/RRF/Haiku-out) was DESIGN-ONLY at W1.1 - config surface landed, implementation is W1.8.
Note on C7: Re-scoped: subset is now an EVAL-TIME ALLOWLIST (consumed at W1.5/W3), not the chunk input - W1.4 chunks the FULL corpus, so subset re-freezes no longer trigger re-chunking. v4 supersedes v3(95)/v2(125, broke cap)/v1(25). Forced-list re-derivation + relabels per the W1.3 audit memo. Does NOT block W1.4 - runs in parallel; only the pin step (W1.4) is a shared touchpoint.
Note on C8: Re-scoped to FULL-corpus chunking + corpus pin. Why: the corpus/ tree is generated from the stale 80-doc CSVs, so 89/95 pilot docs have no file to chunk - regenerate from the canonical xlsx first. Full-corpus chunking decouples the stable chunk store from the churning subset (v3->v4->...), and W1.7 needs the full corpus processed anyway. PIN (snapshot + verify_pin) makes the frozen set verifiable against drift. Runtime index (W1.5) + eval stay subset-only.
Note on C12: Re-scoped from 'tune' to 'BUILD'. Evidence from W1.1: the new architecture (centroids/numpy/RRF, Haiku removal) is NOT implemented anywhere; the live path is the documented Haiku->Sonnet baseline. W1.8 is therefore a build, not a tuning pass. Tail order: W1.8 -> W1.9 -> W1.11 -> W1.10.
Note on C15: NEW row. pilot-baseline (W1.1) was tagged on the OLD architecture (Haiku in path, un-slimmed payload) - anchoring any latency/cost delta on it would be wrong by the Haiku-round-trip + slimming margin. arch-baseline is the clean post-W1.8 anchor. Runs after W1.8 + W1.9, FEEDS W1.10 (memo can't finalize latency targets until these numbers land).

## Pilot Metrics
Pilot Metrics - targets + baseline in Week 1, results in Week 3
Metric | Definition | Target (set W1) | Baseline | Pilot result | Pass?
End-to-end latency p50 | Median total response time across the eval set. | <= ~8.0s p50 (provisional, n=10) | 8044.8 ms (8.0s) - W1.9 warmed | [ ] | [ ]
End-to-end latency p95 | 95th-percentile total response time (worst-case paths show here). | <= ~8.9s p95 (provisional, n=10) | 8928.2 ms (8.9s) - W1.9 warmed | [ ] | [ ]
Time-to-first-token (TTFT) | First-token latency, measured separately from total - streaming can mask slow generation. | p50 ~1.2s / p95 ~2.1s (provisional, n=10) | p50 1207 / p95 2087 ms - W1.9 warmed | [ ] | [ ]
Time-to-first-audio (TTFA) | First audio out for the voice front-end (stream -> sentence-chunk -> TTS). | TBD - set when TTS front-end exists (W2.1) | not measured (no voice/TTS pipeline yet) | [ ] | [ ]
Per-stage latency | Time in input gate / router / retrieval / composer. | hold (path is composer-bound, ~97%) | p50 ms: gate 0.0 / router 164.6 / retrieval 83.2 / composer 7790.2 - W1.9 | [ ] | [ ]
Fabricated citations | Citations not supported by the corpus. Target = 0. | 0 (release requirement) | TBD - W3.x eval harness | [ ] | [ ]
Grounding-fidelity score | Eval-set score for answers grounded in retrieved chunks. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
In-voice register match | register_used vs expected on the eval set. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
AI-governance retrieval | Whether the known retrieval miss is now surfaced. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Out-of-scope handling | Off-taxonomy queries correctly thresholded + declined. | TBD - needs OUT_OF_SCOPE_THRESHOLD calibration (W3.x) | TBD (threshold 0.15 provisional/uncalibrated) | [ ] | [ ]
Routing accuracy | Predicted theme/topic vs the gold doc's topic on the eval set. | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Retrieval recall@k | Share of eval queries with the gold passage in top-k (soft-prior should hold this high even when routing errs). | TBD - W3.x eval harness | TBD - no eval harness yet | [ ] | [ ]
Cost per query | Avg API cost per response - log INPUT vs OUTPUT and CACHED vs UNCACHED; should fall vs baseline. | <= ~$0.017/query cached (provisional) | cached $0.0169 / uncached-equiv $0.0288; caching saves $0.0119 - W1.9 | [ ] | [ ]
Output tokens per answer | Average answer length in tokens - drives cost/latency regardless of payload size. | <= 300 (MAX_TOKENS cap) | median 261, range 131-300 (2 of 10 hit the 300 cap) - W1.9 jsonl | [ ] | [ ]
Theme-A disclaimer present | Share of law-themed responses with the disclaimer. Target = 100%. | TBD - W3.x payload sweep | current locked: tau=0.3, min_k=3, max_k=12, max_tokens=300, lambda=0.25 (untuned) | [ ] | [ ]
Payload knee config | tau / min_k / max_k / chunk budget / max_tokens where quality is flat but cost/latency drop. | dynamic (knee found in W3.x) | 12.0 - all 10 queries saturated MAX_K=12 (cutoff hit ceiling) - W1.9 | [ ] | [ ]
Chunks per query (dynamic) | Avg chunks admitted by the relevance cutoff (score >= tau*top_score, bounded min_k..max_k). | tuned in W3.4 bake-off | locked (untuned): RRF_K=60, topic-bias lambda=0.25 | [ ] | [ ]
Dense/sparse fusion weight | Tuned RRF weighting + topic-bias lambda. | TBD - W3.x eval harness | TBD - no labels yet | [ ] | [ ]
Register-classifier accuracy | Deterministic register vs hand labels. | TBD - gate set in W2.1 | caching present (voice card ephemeral); hit-rate not yet measured | [ ] | [ ]
Prefix cache hit rate | Share of composer calls hitting the cached prefix. | < ~10% (release GATE) | N/A - expand-on-demand built in W2.1 | [ ] | [ ]
Expand-on-demand fire rate | Share of queries needing the whole-doc fallback. Release GATE: fix upstream if > ~10%. | [ set ] | [ ] | [ ] | [ ]
Blue cells are inputs for the team to fill in.